## Slide 1: Project Portfolio Health Review
Prepared automatically by AI Health Agent

## Slide 2: Executive Summary
Portfolio Mix: 1 Red, 0 Amber, 1 Green
Top-line call: Significant schedule slippage observed across multiple projects.
Ask: Review resourcing and blocker resolution for Red projects.

## Slide 3: Portfolio Health At A Glance
Project Name | Status | Top Driver | Data Confidence
S2P Project | Red | Schedule Slippage | High
Project Plan B | Green | Blockers | High

## Slide 4: Cross-Project Trends
Systemic Delay: Schedule Slippage observed across projects (Project_Plan_B, S2P_Project)
  - [S2P_Project] Task 'Zycus - Titan S2P Implementation' is delayed by 51 days.
  - [S2P_Project] Task 'Phase 1- S2C' is delayed by 8 days.
  - [S2P_Project] Task 'Configuration and Build phase' is delayed by 113 days.

## Slide 5: Emerging Risks
S2P_Project: Project is currently Red. Review primary drivers. (Trajectory: insufficient history to assess trajectory)

## Slide 6: Recommendations & Decisions Needed
1. Immediate deep-dive required on all Red projects (S2P_Project) to clear blockers.
2. Investigate schedule estimation accuracy, as >30% of open tasks are delayed.